## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 18 | 14

## Sprint 1 - Day 1
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User should be able to search procedure by name/code
Setup database |  | Karen | In progress | 3 | 2
Cut down the dataset |  | Rauf | Done | 1 | 1
Popuate the database |  | Rauf | Not started | 4 | 0
User should be able to access the website through the internet
Creating result cards (bootstrap) |  | Charlie & Rauf | Done | 7 | 6
Setting up mocha |  | Charlie | Done | 1 | 1
Writing unit tests for cards |  | Charlie | Done | 1 | 1
Writing acceptence test for existing userstories |  | Matt & Daniel | Done | 1 | 1
Wireframing |  | Matt & Daniel | In progress | 8 | 7
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
Others
Updating agile documentation |  | Everyone |  | 10 | 2
Task
Task
Task
Task
Task
Task
TOTAL |  |  |  | 36 | 21 | 0 | 0 | 0 | 0

## Sprint 1 - Day 2
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User should be able to search procedure by name/code
Setup database |  | Karen & Rauf | Done | 3 | 2 | 2
Cut down the dataset |  | Rauf | Done | 1 | 1
Popuate the database |  | Rauf | In progress | 4 |  | 4
Connect to database from Java |  | Karen | In progress | 3 |  | 2
Create data class in java |  | Karen | Done | 1 |  | 1
Create queries in java |  | Karen | In progress | 3 |  | 5
User should be able to access the website through the internet
Creating result cards (bootstrap) |  | Charlie & Rauf | Done | 4 | 3
Setting up mocha |  | Charlie | Done | 1 | 1
Writing unit tests for cards |  | Charlie | Done | 1 | 1
Writing acceptence test for existing userstories |  | Matt & Daniel | Done | 1 | 1
Wireframing |  | Matt & Daniel | In progress | 4 | 5 | 2
Creating Frontend (Nav-bar & side-bar) |  | Matt | In progress | 6 |  | 7
Creating Frontend (Integrating map modal) |  | Matt | In progress | 2 |  | 1
User should be able to view the hospital locations on a map
Creating a map, adding pins |  | Charlie | Done | 3 |  | 5
Geocoding + distance logic |  | Charlie | Not Started | 7 |  | 0
Creating pins from database data |  |  | Not Started
Task
Users should be able to input their location
Geolocation(automatically through browser) |  |  | Not Started
User input manually |  |  | Not Started
Task
Task
Others
Updating agile documentation |  | Daniel | In progress | 10 |  | 2
TOTAL |  |  |  | 54 | 14 | 31 | 0 | 0 | 0

## Sprint 1 - Day 3
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User should be able to search procedure by name/code
Setup database |  | Karen & Rauf | Done | 3 | 2 | 2
Cut down the dataset |  | Rauf | Done | 1 | 1
Popuate the database |  | Rauf | Done | 4 |  | 4 | 4
Connect to database from Java |  | Karen | Done | 3 |  | 2 | 3
Create data class in java |  | Karen | Done | 1 |  | 1
Create queries in java |  | Karen | In progress | 10 |  | 5 | 5
Genrating HTML for cards in Java |  | Charlie | Done | 2 |  |  | 3
User should be able to access the website through the internet
Creating result cards (bootstrap) |  | Charlie & Rauf | Done | 4 | 3
Setting up mocha |  | Charlie | Done | 1 | 1
Writing unit tests for cards |  | Charlie | Done | 1 | 1
Writing acceptence test for existing userstories |  | Matt & Daniel | Done | 1 | 1
Wireframing |  | Matt & Daniel | Done | 4 | 5 | 2
Creating Frontend (Nav-bar & side-bar) |  | Matt | Done | 6 |  | 7
Creating Frontend (Integrating map modal) |  | Matt | Done | 2 |  | 1 | 1
Creating Footer |  | Matt | done | 1 |  |  | 1
User should be able to view the hospital locations on a map
Creating a map, adding pins |  | Charlie | Done | 3 |  | 5
Geocoding + distance logic |  | Charlie | Not Started | 7
Creating pins from database data |  |  | Not Started
Users should be able to input their location
Geolocation(automatically through browser) |  |  | Done | 3 |  |  | 3
User input manually |  |  | Not started
Others
Updating agile documentation |  | Rauf | In progress | 10 |  |  | 1
TOTAL |  |  |  | 67 | 14 | 29 | 21 | 0 | 0

## Sprint 1 - Day 4
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User should be able to search procedure by name/code
Setup database |  | Karen & Rauf | Done | 3 | 2 | 2
Cut down the dataset |  | Rauf | Done | 1 | 1
Popuate the database |  | Rauf | Done | 4 |  | 4 | 4
Connect to database from Java |  | Karen | Done | 3 |  | 2 | 3
Create data class in java |  | Karen | Done | 1 |  | 1
Create queries in java |  | Karen & Daniel | Done | 10 |  | 5 | 5 | 4
Genrating HTML for cards in Java |  | Charlie | Done | 2 |  |  | 3
User should be able to access the website through the internet
Creating result cards (bootstrap) |  | Charlie & Rauf | Done | 4 | 3
Setting up mocha |  | Charlie | Done | 1 | 1
Writing unit tests for cards |  | Charlie | Done | 1 | 1
Writing acceptence test for existing userstories |  | Matt & Daniel | Done | 1 | 1
Wireframing |  | Matt & Daniel | Done | 4 | 5 | 2
Creating Frontend (Nav-bar & side-bar) |  | Matt | Done | 6 |  | 7
Creating Frontend (Integrating map modal) |  | Matt | Done | 2 |  | 1 | 1
Creating Footer |  | Matt | Done | 1 |  |  | 1
Website accessibilty |  | Matt | In progress | 5 |  |  |  | 1
User should be able to view the hospital locations on a map
Creating a map, adding pins |  | Charlie | Done | 3 |  | 5
Geocoding + distance logic |  | Charlie | Not Started | 7
Creating pins from database data |  |  | Not Started
Users should be able to input their location
Geolocation(automatically through browser) |  |  | Done | 3 |  |  | 3
User input manually |  |  | Not started
Others
Updating agile documentation |  | Rauf & Charlie | In progress | 10 |  |  | 1 | 4
Resolving bug in dataset(repopulating databse) |  | Rauf | Done | 1 |  |  |  | 1
Google maps pricing report |  | Charlie | Done | 1 |  |  |  | 1
Preaparing for meetings |  | All | In progress | 2 |  |  |  | 1
TOTAL |  |  |  | 76 | 14 | 29 | 21 | 12 | 0

## Sprint 1 - Day 5
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User should be able to search procedure by name/code
Setup database |  | Karen & Rauf | Done | 3 | 2 | 2
Cut down the dataset |  | Rauf | Done | 1 | 1
Popuate the database |  | Rauf | Done | 4 |  | 4 | 4
Connect to database from Java |  | Karen | Done | 3 |  | 2 | 3
Create data class in java |  | Karen | Done | 1 |  | 1
Create queries in java |  | Karen & Daniel | Done | 10 |  | 5 | 5 | 4
Genrating HTML for cards in Java |  | Charlie | Done | 2 |  |  | 3
User should be able to access the website through the internet
Creating result cards (bootstrap) |  | Charlie & Rauf | Done | 4 | 3
Setting up mocha |  | Charlie | Done | 1 | 1
Writing unit tests for cards |  | Charlie | Done | 1 | 1
Writing acceptence test for existing userstories |  | Matt & Daniel | Done | 1 | 1
Wireframing |  | Matt & Daniel | Done | 4 | 5 | 2
Creating Frontend (Nav-bar & side-bar) |  | Matt | Done | 6 |  | 7
Creating Frontend (Integrating map modal) |  | Matt | Done | 2 |  | 1 | 1
Creating Footer |  | Matt | Done | 1 |  |  | 1
Website accessibilty |  | Matt | In progress | 5 |  |  |  | 1 | 2
User should be able to view the hospital locations on a map
Creating a map, adding pins |  | Charlie | Done | 3 |  | 5
Geocoding + distance logic |  | Charlie | Not Started | 7
Creating pins from database data |  |  | Not Started
Users should be able to input their location
Geolocation(automatically through browser) |  |  | Done | 3 |  |  | 3
User input manually |  |  | Not started
Others
Updating agile documentation |  | Rauf & Charlie | In progress | 10 |  |  | 1 | 4 | 6
Resolving bug in dataset(repopulating databse) |  | Rauf | Done | 1 |  |  |  | 1
Google maps pricing report |  | Charlie | Done | 1 |  |  |  | 1
Preaparing for meetings |  | All | Done | 2 |  |  |  | 1 | 2
TOTAL |  |  |  | 76 | 14 | 29 | 21 | 12 | 10