## Agile Product Backlog
AGILE PRODUCT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
|  | Sprint 1 | [6 empty] | In Progress | 64
1 | User should be able to search procedure by name | " " |  |  |  | Yes | No | High | Not Started | 5 | Yes | This section is for the drop-down list
2 | User should be able to search procedure by procedure code | " " |  |  |  | Yes | No | Medium | Not Started | 4 | Yes | Yes | High | Complete | Charlie Hewitt
3 | User should be able to change the sort by distance | " " |  |  |  | Yes | No | High | Not Started | 8 | Yes | No | Medium | In Progress | Rauf Tarar Sultana
4 | User should be able to change the sort by price | " " |  |  |  | Yes | No | High | Not Started | 8 | Yes |  | Low | Not Started | Matt Robb
5 | User should be able to change the sort by custom rating | " " |  |  |  | Yes | No | Medium | Not Started | 12 | Yes |  |  |  | Daniel Scheitler
6 | User should be able to view the hospital locations on a map | " " |  |  |  | Yes | No | Low | Not Started | 5 | Yes |  |  |  | Mengqi Jiang
7 | User should be able to filter results based on price range | " " |  |  |  | Yes | No | Medium | Not Started | 5 | Yes
8 | User should be able to filter results based on distance | " " |  |  |  | Yes | No | Medium | Not Started | 5 | Yes
9 | User with account should be able to leave review | " " |  |  |  | Yes | No | Low | Not Started | ??? | Yes
10 | Users should be able to input their location manually | " " |  |  |  | Yes | No | High | Not Started | ??? | Yes
11 | Users should be able to to provide their location automatically |  |  |  |  | Yes | No | Medium | Not Started | ??? | Yes
12 | User should be able to access the web application from a mobile phone with a responsive design | " " |  |  |  | Yes | No | Low | Not Started | ??? | Yes
13 | User must be able to adjust size and contrast of text on the page | " " |  |  |  | Yes | No | Medium | Not Started | ??? | Yes
14 | Users who are colour-blind/blind should have the option for text-to-speech or colour-filters | " " |  |  |  | Yes | No | Low | Not Started | ??? | Yes
15 | Users should have the option to create an account | " " |  |  |  | Yes | No | Low | Not Started | ??? | Yes
16 | User should have option to store their search criteria | " " |  |  |  | Yes | No | Low | Not Started | ??? | Yes
17 | The admin should be able to login | " " |  |  |  | Yes | No | Medium | Not Started | ??? | Yes
18 | The admin should be able to add new data to existing records | " " |  |  |  | Yes | No | Medium | Not Started | 4 | Yes
19 | The admin should be able to update data of existing hospitals | " " |  |  |  | Yes | No | Medium | Not Started | 5 | Yes
20 | The admin should be able to delete data of existing hospitals | " " |  |  |  | Yes | No | Medium | Not Started | 3 | Yes
21 | The admin should be able to import an excel file to bulk add/update data in the database | " " |  |  |  | Yes | No | Medium | Not Started | ??? | Yes
Sprint 2