## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 18 | 14

## Sprint 1 - Day 1
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User should be able to search procedure by name/code
Setup database |  | Karen | In progress | 3 | 2
Cut down the dataset |  | Rauf | Done | 1 | 1
Popuate the database |  | Rauf | Not started | 4 | 0
User should be able to access the website through the internet
Creating result cards (bootstrap) |  | Charlie & Rauf | Done | 7 | 6
Setting up mocha |  | Charlie | Done | 1 | 1
Writing unit tests for cards |  | Charlie | Done | 1 | 1
Writing acceptence test for existing userstories |  | Matt & Daniel | Done | 1 | 1
Wireframing |  | Matt & Daniel | In progress | 8 | 7
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
Others
Updating agile documentation |  | Everyone |  | 10 | 2
Task
Task
Task
Task
Task
Task
TOTAL |  |  |  | 36 | 21 | 0 | 0 | 0 | 0

## Sprint 2 - Day 1
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Accessibility
User must be able to adjust size and contrast of text on the page |  | Matt | In Progress | 5 | 5
Users who are colour-blind/blind should have the option for text-to-speech or colour-filters |  | Matt | Not Started | 6 | 6
colour-filters |  | Matt | Not Started | 5 | 5
User should be able to access the web application from a mobile phone with a responsive design |  | Matt | In Progress | 10 | 4
Distance features
User should be able to change the sort by distance |  | Charlie | Not Started | 10 | 10
User should be able to filter results based on distance |  | Charlie | Not Started | 5 | 5
Creating pins from database data |  |  | Not Started
Geocoding + distance logic |  | Charlie | Not Started | 7 | 6
Users should be able to input their location manually |  | Charlie | Not Started | 3 | 3
Connecting Backend to the frontend
Conecting the search bar with back end to give the functionality of search |  | Karen | In progress | 5 | 5
Connecting the result cards with the backend |  | Karen | In progress | 4 | 4
Connecting filters |  |  | Not Started | 8 | 8
Others
Updating agile documentation |  | Rauf | In progress | 10 | 7
Sprint retrospective |  | Daniel | In progress | 5 | 1
TOTAL |  |  |  | 83 | 69 | 0 | 0 | 0 | 0