## Sprint 2 - Day 1
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Accessibility
User must be able to adjust size and contrast of text on the page |  | Matt | In Progress | 5 | 5
Users who are colour-blind/blind should have the option for text-to-speech or colour-filters |  | Matt | Not Started | 6 | 6
colour-filters |  | Matt | Not Started | 5 | 5
User should be able to access the web application from a mobile phone with a responsive design |  | Matt | In Progress | 10 | 4
Distance features
User should be able to change the sort by distance |  | Charlie | Not Started | 10 | 10
User should be able to filter results based on distance |  | Charlie | Not Started | 5 | 5
Creating pins from database data |  |  | Not Started
Geocoding + distance logic |  | Charlie | Not Started | 7 | 6
Users should be able to input their location manually |  | Charlie | Not Started | 3 | 3
Connecting Backend to the frontend
Conecting the search bar with back end to give the functionality of search |  | Karen | In progress | 5 | 5
Connecting the result cards with the backend |  | Karen | In progress | 4 | 4
Connecting filters |  |  | Not Started | 8 | 8
Others
Updating agile documentation |  | Rauf | In progress | 10 | 7
Sprint retrospective |  | Daniel | In progress | 5 | 1
TOTAL |  |  |  | 83 | 69 | 0 | 0 | 0 | 0

## Sprint 2 - Day 2
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Accessibility
User must be able to adjust size and contrast of text on the page |  | Matt | In Progress | 5 | 5 | 5
Users who are colour-blind/blind should have the option for text-to-speech or colour-filters |  | Matt | Not Started | 6 | 6 | 6
colour-filters |  | Matt | Not Started | 5 | 5 | 5
User should be able to access the web application from a mobile phone with a responsive design |  | Matt | In Progress | 10 | 4 | 1
Distance features
User should be able to change the sort by distance |  | Charlie | Not Started | 10 | 10 | 5
User should be able to filter results based on distance |  | Charlie | Not Started | 5 | 5 | 5
Creating pins from database data |  |  | Not Started
Users should be able to input their location manually |  | Charlie | Not Started | 3 | 3 | 3
Connecting Backend to the frontend
Conecting the search bar with back end to give the functionality of search |  | Karen | In progress | 5 | 5 | 0
Connecting the result cards with the backend |  | Karen | In progress | 4 | 4 | 2
Connecting filters |  |  | Not Started | 8 | 8 | 8
Others
Updating agile documentation |  | Rauf | In progress | 10 | 7 | 5
Sprint retrospective |  | Daniel | Complete | 5 | 1 | 0
Travis setup |  | Rauf | In progress | 4 | 4 | 2
List of actions (based on retrospective) |  | Daniel | In progress | 2 | 2 | 1
Report on unit test video |  | Charlie | Not Started | 2 | 2 | 2
TOTAL |  |  |  | 84 | 71 | 50 | 0 | 0 | 0