## Agile Product Backlog
AGILE PRODUCT BACKLOG
USERSTORY ID | Userstory | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
|  | Sprint 1 | [6 empty] | In Progress | 90
1 | As a user should be able to search procedure by name | Sprint 1 | Mengqi Jiang | 2020-01-29 | 2020-01-29 | Yes | Yes | High | Done | 5 | Yes | This section is for the drop-down list
2 | User should be able to search procedure by procedure code | Sprint 1 | Daniel Scheitler | 2020-01-30 | 2020-01-30 | Yes | Yes | High | Done | 4 | Yes | Yes | High | Complete | Charlie Hewitt
3 | User should be able to change the sort by price | Sprint 1 | Daniel Scheitler | 2020-01-30 | 2020-01-30 | Yes | Yes | High | Done | 8 | Yes | No | Medium | In Progress | Rauf Tarar Sultana
8 | User should be able to access the website through the internet | Sprint 1 | Charlie Hewitt | 2020-01-30 |  | Yes | Yes | High | In Progress | 5 | Yes
9 | Set up the database | Sprint 1 | Rauf Tarar | 2020-01-28 | 2020-01-28 | No | Yes | High | Complete | 1 | Yes
10 | Populate the database | Sprint 1 | Rauf Tarar | 2020-01-28 | 2020-01-30 | No | Yes | High | Complete | 5 | Yes
5 | User should be able to filter results based on price range | Sprint 1 | Mengqi Jiang | 2020-01-30 | 2020-01-30 | Yes | Yes | Medium | Done | 5 | Yes
6 | Users should be able to to provide their location automatically | Sprint 1 | Charlie Hewitt | 2020-01-29 | 2020-01-29 | Yes | Yes | Medium | Done | 4 | Yes
11 | Wireframing | Sprint 1 | Matt Robb | 2020-01-28 | 2020-01-30 | No | Yes | Medium | Complete | 10 | Yes
12 | User should be able to filter results based on distance | Sprint 2 | Charlie Hewitt | 2020-02-05 |  | Yes | Yes | Medium | Not Started | 5 | Yes
1 | User must be able to adjust size and contrast of text on the page | Sprint 2 | Matt Robb | 2020-02-03 |  | Yes | Yes | Medium | In Progress | 5 | Yes
10 | User should be able to change the sort by distance | Sprint 2 | Charlie Hewitt | 2020-02-05 |  | Yes | Yes | Medium | Not Started | 10 | Yes
12 | Research on cookies | Sprint 1 | Daniel Scheitler | 2020-01-29 | 2020-01-29 | No | Yes | Low | Complete | 3 | Yes
4 | User should be able to view the hospital locations on a map | Sprint 1 | Charlie Hewitt | 2020-01-28 | 2020-02-06 | Yes | Yes | Low | In Progress | 10 | Yes
7 | User should be able to access the web application from a mobile phone with a responsive design | Sprint 1 | Matt Robb | 2020-01-30 |  | Yes | Yes | Low | In Progress | 10 | Yes
2 | Users who are colour-blind/blind should have the option for text-to-speech or colour-filters | Sprint 2 | Matt Robb |  |  | Yes | Yes | Low | Not Started | 6 | Yes
| colour-filters | Sprint 3 | Matt Robb |  |  |  |  | Low | Not Started | 5 | Yes
3 | Users should have the option to create an account | Sprint 2 | No one |  |  | Yes | Yes | Low | Not Started | 6 | No
4 | User should have option to store their search criteria | Sprint 2 | No one |  |  | Yes | Yes | Low | Not Started | 7 | No
5 | The admin should be able to login | Sprint 2 | No one |  |  | Yes | No | Low | Not Started | 10 | No
6 | The admin should be able to add new data to existing records | Sprint 2 | No one |  |  | Yes | No | Low | Not Started | 4 | No
7 | The admin should be able to update data of existing hospitals | Sprint 2 | No one |  |  | Yes | No | Low | Not Started | 5 | No
8 | The admin should be able to delete data of existing hospitals | Sprint 2 | No one |  |  | Yes | No | Low | Not Started | 3 | No
9 | The admin should be able to import an excel file to bulk add/update data in the database | Sprint 2 | No one |  |  | Yes | Yes | Low | Not Started | 4 | No
11 | User should be able to change the sort by custom rating | Sprint 2 | No one |  |  | Yes | No | Low | Not Started | 5 | No
13 | User should be able to leave review | Sprint 2 | No one |  |  | Yes | Yes | Low | Not Started | 6 | No
14 | User shoulf be able to see previous reviews | Sprint 2 | Mengqi Jiang |  |  | Yes | Yes | Low | Not Started | 6 | Yes
15 | Users should be able to input their location manually | Sprint 2 | Charlie Hewitt |  |  | Yes | Yes | Low | Not Started | 3 | Yes